## Product Backlog
Ansh Mishra | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Set up development environment: Install Java 17, Maven, VS Code, Spring Boot CLI, MongoDB, and configure JDBC connector | MUST HAVE | NA | Ansh Mishra | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Understand OOP concepts in Java Study classes, objects, encapsulation, inheritance, polymorphism, abstraction relevant to banking domain | MUST HAVE | NA | Ansh Mishra | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Workflow creation and project goal document: Define system modules, data flow, and feature list for Banking Activity Simulation Platform | MUST HAVE | US-02 | Ansh Mishra | 3- Completed
Sprint 2 | Sprint 2 | US-04 | Create Spring Boot project structure: Initialize Maven project, configure application.properties, set up package hierarchy (controller, service, model, repository) | MUST HAVE | US-01 | Ansh Mishra | 3- Completed
Sprint 2 | Sprint 2 | US-05 | Design and implement Account model: Create Account.java POJO with fields (accountId, holderName, balance, status) using OOP encapsulation | MUST HAVE | US-04 | Ansh Mishra | 3- Completed
Sprint 2 | Sprint 2 | US-06 | Implement AccountService: Add business logic for create account, get account, update balance, delete account operations | MUST HAVE | US-05 | Ansh Mishra | 3- Completed
Sprint 2 | Sprint 2 | US-07 | Implement AccountController: Expose REST endpoints (POST /accounts, GET /accounts/{id}, GET /all-accounts) and test with Postman | MUST HAVE | US-06 | Ansh Mishra | 3- Completed
Sprint 3 | Sprint 3 | US-08 | Design MongoDB schema: Define collections: accounts, transactions; configure MongoRepository and connect Spring Boot with MongoDB | MUST HAVE | US-04 | Ansh Mishra | 3- Completed
Sprint 3 | Sprint 3 | US-09 | Implement Deposit functionality: Create DepositRequest DTO, service method to add funds and persist Transaction record in MongoDB | MUST HAVE | US-08 | Ansh Mishra | 3- Completed
Sprint 3 | Sprint 3 | US-10 | Implement Withdrawal functionality: Create WithdrawRequest DTO, validate sufficient balance, deduct funds, record transaction | MUST HAVE | US-09 | Ansh Mishra | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Implement Transfer functionality: Atomic transfer between accounts: debit source, credit target, create linked Transaction document | MUST HAVE | US-10 | Ansh Mishra | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Implement Transaction history: GET /transactions/{accountId} endpoint returning chronological list of all transactions for an account | SHOULD HAVE | US-11 | Ansh Mishra | 3- Completed
Sprint 4 | Sprint 4 | US-13 | Implement Alert module: Add AlertService to monitor transactions exceeding defined thresholds; log high-value activity server-side | SHOULD HAVE | US-11 | Ansh Mishra | 3- Completed
Sprint 4 | Sprint 4 | US-14 | Implement global exception handling: Create InsufficientFundsException, AccountNotFoundException; configure @ControllerAdvice with standardised JSON error responses | MUST HAVE | US-07 | Ansh Mishra | 3- Completed
Sprint 4 | Sprint 4 | US-15 | Service layer unit testing: Write JUnit/Postman test cases for AccountService, TransactionService; validate deposit, withdraw, transfer, and exception flows | MUST HAVE | US-12 | Ansh Mishra | 3- Completed
Sprint 4 | Sprint 4 | US-16 | End-to-end backend integration test: Test all REST API endpoints together; verify real-time balance updates, transaction records, and error handling | MUST HAVE | US-15 | Ansh Mishra | 3- Completed
Sprint 5 | Sprint 5 | US-17 | Build frontend foundation: Set up React + Vite project; configure Tailwind CSS, directory structure (pages, components, services) | SHOULD HAVE | US-16 | Ansh Mishra | 3- Completed
Sprint 5 | Sprint 5 | US-18 | Develop Landing Page: Create premium dark-theme landing page with feature highlights, navigation, and call-to-action using HTML/Tailwind | SHOULD HAVE | US-17 | Ansh Mishra | 3- Completed
Sprint 5 | Sprint 5 | US-19 | Develop Dashboard page: Display all accounts with real-time balance overview, recent transactions activity centre, and quick action buttons | MUST HAVE | US-17 | Ansh Mishra | 3- Completed
Sprint 5 | Sprint 5 | US-20 | Implement Account Form modal: React modal component for creating new accounts; form validation, submit to POST /accounts API | MUST HAVE | US-19 | Ansh Mishra | 3- Completed
Sprint 5 | Sprint 5 | US-21 | Implement Transaction modal: Unified React form for Deposit, Withdrawal, Transfer; connects to respective Spring Boot endpoints via Axios | MUST HAVE | US-20 | Ansh Mishra | 3- Completed
Sprint 6 | Sprint 6 | US-22 | Frontend-Backend API integration: Connect all React components to Spring Boot REST APIs using Axios; verify real-time data reflection on UI | MUST HAVE | US-21 | Ansh Mishra | 3- Completed
Sprint 6 | Sprint 6 | US-23 | Implement account detail page: Show individual account transaction history, balance, status; fetch data via GET /accounts/{id} API | SHOULD HAVE | US-22 | Ansh Mishra | 3- Completed
Sprint 6 | Sprint 6 | US-24 | Frontend routing setup: Configure React Router DOM for SPA navigation (/, /dashboard, /account/:id); eliminate full-page reloads | MUST HAVE | US-23 | Ansh Mishra | 3- Completed
Sprint 6 | Sprint 6 | US-25 | Cross-module end-to-end testing: Perform full-flow testing: create account → deposit → transfer → view history; check UI reflects API data in real time | MUST HAVE | US-24 | Ansh Mishra | 3- Completed
Sprint 7 | Sprint 7 | US-26 | Deploy backend on Render and frontend on Vercel. Configure environment variables and API connectivity. Test all routes and endpoints in production. | MUST HAVE | US-25 | Ansh Mishra | 3- Completed
Sprint 7 | Sprint 7 | US-27 | Documentation completion: Finalise SRS document, project report, Agile document, and README with setup instructions | SHOULD HAVE | US-26 | Ansh Mishra | 3- Completed
Sprint 8 | Sprint 8 | US-28 | User authentication: Implement Spring Security + JWT login/logout; role-based access (Admin vs Customer) | COULD HAVE | US-26 | Ansh Mishra | 2- In Progress
Sprint 8 | Sprint 8 | US-29 | Email notification integration: Configure SMTP alerts for high-value transactions | COULD HAVE | US-13 | Ansh Mishra | 1- Pending
Sprint 8 | Sprint 8 | US-30 | Analytics dashboard: Integrate Recharts for spending pattern visualisations | WON'T HAVE | US-22 | Ansh Mishra | 1- Pending
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTE: Task sizing should be between 0.5 to 12 hours per task
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Est. Effort (45 Hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42 | Day 43 | Day 44 | Day 45
SPRINT 1 BACKLOG (FEB 16 – 23 , 2026)
US-01 | T-01 | Install Java 17, Maven, Spring Boot CLI, VS Code extensions | 2026-02-16 | 2026-02-16 | Ansh Mishra | Setup | 3- Completed | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-01 | T-02 | Install and configure MongoDB; test connection with MongoCompass | 2026-02-17 | 2026-02-17 | Ansh Mishra | Setup | 3- Completed | 1.5 | Day 1: 0; Day 2: 1.5; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-02 | T-03 | Study OOP concepts: classes, objects, encapsulation, inheritance, polymorphism in Java | 2024-12-18 | 2024-12-22 | Ansh Mishra | Learning | 3- Completed | 10 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 2; Day 5: 1; Day 6: 2; Day 7: 1; Day 8: 2; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-03 | T-04 | Create workflow diagram and project goal document using LucidChart | 2024-02-23 | 2026-02-23 | Ansh Mishra | Design | 3- Completed | 2 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 2; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
SPRINT 2 BACKLOG (FEB 24–28, 2026)
US-04 | T-05 | Initialize Spring Boot Maven project; configure application.properties for MongoDB | 2026-02-24 | 2026-02-24 | Ansh Mishra | Setup | 3- Completed | 2 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 2; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-05 | T-06 | Design Account.java POJO with OOP: private fields, getters/setters, constructors | 2026-02-25 | 2026-02-25 | Ansh Mishra | Coding | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 2; Day 10: 2; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-06 | T-07 | Implement AccountService: createAccount, findById, updateBalance, deleteAccount methods | 2026-02-27 | 2026-02-28 | Ansh Mishra | Coding | 3- Completed | 5 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 1; Day 11: 2; Day 12: 2; Day 13: 0; Day 14: 0
US-07 | T-08 | Implement AccountController REST endpoints; test POST and GET APIs via Postman | 2026-02-28 | 2026-02-28 | Ansh Mishra | Coding | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 2; Day 14: 0
SPRINT 3 BACKLOG (MAR 1–6, 2026) | [8 empty] | Day 14: 2
US-08 | T-09 | Define MongoDB collections: accounts and transactions; configure MongoRepository interfaces | 2026-03-01 | 2026-03-01 | Ansh Mishra | Build | 3- Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-09 | T-10 | Implement DepositService: validate input, add balance, create Transaction document in MongoDB | 2026-03-02 | 2026-03-02 | Ansh Mishra | Coding | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 1; Day 6: 2; Day 7: 1; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-10 | T-11 | Implement WithdrawalService: check balance sufficiency, deduct funds, persist transaction record | 2026-03-03 | 2026-03-03 | Ansh Mishra | Coding | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 2; Day 9: 2; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-11 | T-12 | Implement TransferService: atomic debit + credit across two accounts; create linked transaction | 2026-03-04 | 2026-03-04 | Ansh Mishra | Coding | 3- Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 2; Day 8: 1; Day 9: 1; Day 10: 1; Day 11: 0; Day 12: 1; Day 13: 0; Day 14: 0
US-12 | T-13 | Implement GET /transactions/{accountId} endpoint; return sorted transaction history | 2026-03-06 | 2026-03-06 | Ansh Mishra | Coding | 3- Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 1; Day 7: 1; Day 8: 1; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
SPRINT 4 BACKLOG (MAR 7–12, 2026)
US-13 | T-14 | Implement AlertService: detect transactions above threshold; log alerts to console | 2026-03-07 | 2026-03-08 | Ansh Mishra | Build | 3- Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 1; Day 8: 1; Day 9: 1; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-14 | T-15 | Create custom exceptions: InsufficientFundsException, AccountNotFoundException; configure @ControllerAdvice | 2026-03-09 | 2026-03-09 | Ansh Mishra | Coding | 3- Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-15 | T-16 | Write JUnit test cases for AccountService and TransactionService; run Postman collection | 2026-03-10 | 2026-03-11 | Ansh Mishra | System Test | 3- Completed | 5 | Day 1: 0; Day 2: 0; Day 3: 1; Day 4: 0; Day 5: 2; Day 6: 0; Day 7: 1; Day 8: 1; Day 9: 1; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-16 | T-17 | Full backend integration test: create → deposit → transfer → history flow; fix bugs | 2026-03-12 | 2026-03-12 | Ansh Mishra | Integration Test | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 20; Day 7: 0; Day 8: 1; Day 9: 1; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
SPRINT 5 BACKLOG (MAR 13–17, 2026)
US-17 | T-18 | Set up React + Vite project; install Tailwind CSS, Axios, React Router DOM | 2026-03-13 | 2026-03-13 | Ansh Mishra | Setup | 3- Completed | 2 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-18 | T-19 | Build Landing Page with Tailwind: hero section, feature cards, CTA, dark theme | 2026-03-14 | 2026-03-15 | Ansh Mishra | Coding | 3- Completed | 5 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 1; Day 8: 1; Day 9: 2; Day 10: 1; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-19 | T-20 | Build Dashboard page: account cards, balance summary, recent activity list | 2026-03-16 | 2026-03-17 | Ansh Mishra | Coding | 3- Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 2; Day 8: 0; Day 9: 2; Day 10: 0; Day 11: 2; Day 12: 0; Day 13: 0; Day 14: 0
US-20 | T-21 | Create AccountForm modal: input fields, form validation, POST /accounts call via Axios | 2026-03-17 | 2026-03-17 | Ansh Mishra | Coding | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 2; Day 8: 0; Day 9: 2; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
SPRINT 6 BACKLOG (MAR 18–25, 2026)
US-21 | T-22 | Build Transaction modal: deposit/withdraw/transfer tabs; connect to Spring Boot APIs via Axios | 2026-03-18 | 2026-03-19 | Ansh Mishra | Coding | 3- Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-22 | T-23 | API integration: connect all React pages to backend; verify real-time balance and history updates | 2026-03-20 | 2026-03-21 | Ansh Mishra | Integration Test | 3- Completed | 5 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 1; Day 7: 0; Day 8: 2; Day 9: 0; Day 10: 1; Day 11: 2; Day 12: 0; Day 13: 0; Day 14: 0
US-23 | T-24 | Build Account Detail page: fetch individual account + transaction history; display formatted | 2026-03-22 | 2026-03-22 | Ansh Mishra | Coding | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 1; Day 8: 1; Day 9: 2; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-24 | T-25 | Configure React Router: set up routes /, /dashboard, /account/:id; test SPA navigation | 2026-03-23 | 2026-03-23 | Ansh Mishra | Coding | 3- Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 1; Day 9: 1; Day 10: 1; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
US-25 | T-26 | End-to-end UI test: create account → deposit → transfer → view history → verify on screen | 2026-03-24 | 2026-03-25 | Ansh Mishra | System Test | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 1; Day 5: 0; Day 6: 2; Day 7: 0; Day 8: 1; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0
SPRINT 7 BACKLOG (MAR 26–30, 2026)
US-26 | T-27 | Deploy Spring Boot backend; deploy React frontend; perform smoke testing on live environment | 2026-03-26 | 2026-03-27 | Ansh Mishra | Deployment | 3- Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 8: 0; Day 9: 0; Day 10: 2; Day 11: 2; Day 12: 2; Day 13: 0; Day 14: 0
US-27 | T-28 | Finalise all documentation: SRS, project report, Agile doc, README with setup guide | 2026-03-28 | 2026-03-30 | Ansh Mishra | Others | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 2; Day 13: 2; Day 14: 0
SPRINT 8 BACKLOG (MAR 2025 – Future)
US-28 | T-29 | Implement Spring Security + JWT authentication; role-based access for Admin and Customer | 2026-04-01 | 2026-04-07 | Ansh Mishra | Coding | 2- In Progress | 8 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 1; Day 11: 2; Day 12: 3; Day 13: 2; Day 14: 0
US-29 | T-30 | Configure SMTP email notifications for high-value transaction alerts | 08-Feb-2025 | 10-Feb-2025 | Ansh Mishra | Build | 1- Pending | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 2; Day 12: 0; Day 13: 0; Day 14: 0
US-30 | T-31 | Integrate Recharts analytics dashboard for spending pattern visualisation | 11-Feb-2025 | 15-Feb-2025 | Ansh Mishra | Coding | 1- Pending | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0; Day 9: 0; Day 10: 0; Day 11: 0; Day 12: 0; Day 13: 0; Day 14: 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Confusion about which version of Java and Maven to install for Spring Boot compatibility | Mentor clarified to use Java 17 LTS and Maven 3.8+; students updated their local setups
Sprint 1 | Day 3 | Difficulty understanding abstract classes vs interfaces in OOP for banking domain | Reviewed examples with Account and Transaction abstractions; mentor walked through code examples
Sprint 2 | Day 8 | Spring Boot project not starting port conflict and MongoDB connection refused | Fixed port to 8080 in application.properties; verified MongoDB service was running on port 27017
Sprint 2 | Day 10 | AccountService methods returning null MongoRepository not injected correctly | Fixed missing @Service and @Autowired annotations; verified Spring context was loading beans
Sprint 3 | Day 15 | Transfer logic causing negative balance race condition between debit and credit | Added balance sufficiency check before debit; reviewed @Transactional usage for atomicity
Sprint 3 | Day 17 | MongoDB transactions failing replica set not configured for multi-document atomicity | Simplified approach: sequential operations with rollback logic in catch block
Sprint 4 | Day 22 | Exception handler not returning proper JSON returning HTML error page instead | Configured @ControllerAdvice with @ResponseBody and proper MediaType headers
Sprint 4 | Day 25 | JUnit tests failing due to test data pollution between test methods | Added @BeforeEach to reset test data and used in-memory MongoDB for isolated test runs
Sprint 5 | Day 33 | Tailwind CSS not applying styles PostCSS config missing in Vite setup | Added tailwind.config.js and postcss.config.js; restarted dev server to apply changes
Sprint 5 | Day 36 | Axios requests failing with CORS error when calling Spring Boot from React | Added @CrossOrigin annotation to all controllers; set allowed origins in Spring config
Sprint 6 | Day 40 | Transaction modal not reflecting updated balance after submission | Fixed by calling fetchAccounts() after successful API response to refresh state
Sprint 6 | Day 44 | React Router not matching /account/:id routes blank page on navigation | Fixed import paths and ensured BrowserRouter wrapped App component in main.jsx
Sprint 7 | Day 50 | Backend deployment failing on cloud MongoDB URI not set in environment | Added MONGO_URI environment variable in deployment config; verified connection string format
Sprint 8 | Day 55 | JWT authentication not persisting token lost on page refresh | Implemented localStorage token storage with Axios interceptor to attach header on each request

## Retrospection
SL #+G8A1:H1A1:I9 | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 2026-02-16 | 2026-02-23 | Ansh Mishra | Reading official Spring Boot and MongoDB documentation before each session | Jumping into code without understanding OOP concepts first | Attending all mentor sessions and taking notes | Dedicated 30 minutes before each class to review OOP fundamentals
2 | Sprint 2 | 2026-02-24 | 2026-02-28 | Ansh Mishra | Testing each REST endpoint immediately after building it using Postman | Skipping service layer and writing logic directly in the controller | Asking for help when stuck rather than spending hours alone | Set up a shared Postman collection to test endpoints consistently
3 | Sprint 3 | 2026-03-01 | 2026-03-06 | Ansh Mishra | Validating edge cases (zero balance, negative amounts) before committing code | Assuming MongoDB operations are atomic without verifying | Breaking down complex features (transfer) into smaller steps | Added explicit balance check before every withdrawal/transfer operation
4 | Sprint 4 | 2026-03-07 | 2026-03-12 | Ansh Mishra | Writing unit tests alongside feature development, not after | Hardcoding test data inside service methods instead of using DTOs | Using @ControllerAdvice for all exception handling | Refactored all exception handling to a single GlobalExceptionHandler class
5 | Sprint 5 | 2026-03-13 | 2026-03-17 | Ansh Mishra | Configuring React project structure and Tailwind before building components | Writing inline styles; using Tailwind utility classes consistently instead | Referencing component library docs (Lucide React) for icons | Set up a shared component folder and reusable Button/Card components
6 | Sprint 6 | 2026-03-18 | 2026-03-25 | Ansh Mishra | Using useEffect to refresh data after every API mutation | Letting API errors fail silently; adding visible toast error messages | Following React Router conventions for all navigation | Added Axios interceptors for global error handling across all requests
7 | Sprint 7 | 2026-03-26 | 2026-03-30 | Ansh Mishra | Testing in deployment environment before marking tasks complete | Assuming local-tested code works in cloud without verification | Maintaining updated README with clear setup instructions | Created deployment checklist; all environment variables documented
8 | Sprint 8 | 2026-04-01 | 2026-04-15 | Ansh Mishra | Planning authentication flow before implementation using sequence diagrams | Storing sensitive tokens in memory; using secure httpOnly cookies approach | Iterating on existing working modules without breaking them | Feature-branch development with PR reviews before merging to main